## Task_Tracker
Week | Task | Status (Pending/Done) | Deadline (Day) | Notes
Week 1 | Download & preprocess Malimg dataset |  | Day 1-2
Week 1 | Create family-wise distribution split |  | Day 3
Week 1 | Implement baseline CNN |  | Day 4
Week 1 | Train & evaluate baseline (ID & OOD) |  | Day 5-7
Week 2 | Implement contrastive encoder |  | Day 8-9
Week 2 | Implement NT-Xent loss |  | Day 10
Week 2 | Pretrain encoder (self-supervised) |  | Day 11-12
Week 2 | Fine-tune classifier |  | Day 13-14
Week 3 | Run 80/20 family split experiment |  | Day 15
Week 3 | Run 60/40 family split experiment |  | Day 16
Week 3 | Run 50/50 family split experiment |  | Day 17
Week 3 | Generate degradation & embedding plots |  | Day 18-21
Week 4 | Write research report draft |  | Day 24-27
Week 4 | Finalize GitHub & documentation |  | Day 28-30

## Metrics_Template
Model | Train_Families_% | In_Distribution_Accuracy | OOD_Accuracy
Baseline_CNN | 70 | 0.95 | 0.62
Contrastive_Model | 70 | 0.93 | 0.78
Baseline_CNN | 50 | 0.92 | 0.48
Contrastive_Model | 50 | 0.9 | 0.7